## Sheet1
Second Language Teaching MA
Project Report Timeline
Student:
| 2021-07-16 | Goal for Defense: (Type in MM/DD/YYYY)
Days Left | Due Date | Task | Person | No. of Days
-30 | 2021-02-23 | Give Chair Proposal | Chair | 3
|  | Make Revisions on Proposal | Student
-27 | 2021-02-26 | Give Committee Proposal | Committee | 14
|  | Proposal Defense | Everyone | NA
|  | Make Revisions on Proposal | Student | 2
-11 | 2021-03-14 | Give Committee Final Draft of Proposal | Student | 2
|  | Write First Draft of IRB Protocol | Student | 7
-2 | 2021-03-23 | Give Chair Draft of IRB Protocol | Chair | 3
|  | Make Revisions on IRB Protocol and Submit | Student | 2
3 | 2021-03-28 | Give Chair Introduction | Chair | 3
|  | Make Revisions on Purpose/Introduction | Student | 2
8 | 2021-04-02 | Give Chair References | Chair | 3
|  | Make Revisions on References | Student | 3
|  | Work on Project Deliverables | Student | 30
44 | 2021-05-08 | Give Chair Methodology Section | Chair | 3
|  | Make Revisions to Methodology Section | Student | 2
|  | Perform Analysis | Student | 14
63 | 2021-05-27 | Give Chair Findings Section | Chair | 3
|  | Make Revisions on Findings | Student | 2
68 | 2021-06-01 | Give Chair Literature Review | Chair | 3
|  | Make Revisions on Literature Review | Student | 2
73 | 2021-06-06 | Give Chair Introduction, Plan of Action and Conclusion | Chair | 3
|  | Make Revisions on Introduction, Plan of Action and Conclusion | Student | 2
78 | 2021-06-11 | Give Chair Complete Draft of Project Report | Chair | 3
|  | Make Revisions Complete Draft of Project | Student | 2
83 | 2021-06-16 | Give Committee Chair Approved Complete Draft of Project Report | Committee | 14
|  | Make Revisions based on Committee Recommendations | Student | 2
113 | 2021-07-02 | Get Approval from Committee for Defense | Committee needs defendable copy | NA
|  | Give Committee Defense-Ready Project Report | Committee needs defendable copy | 14
113 | 2021-07-16 | Project Defense
|  | Make Revisions on Project Report | Student | 7
134 | 2021-08-06 | Turn in Final Project Report for Department Approval | Student
Formulas:
Days Left = ([Due Date]-TODAY())
Due Date = B37-SUM([No. of Days]:E37)
Due Date = B37-SUM([No. of Days, row below]:E37)
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If IRB approval is not needed, delete the section below and move directly to writing the Introduction
Note on E38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There is no minimum timeline for this so the amount of time devoted to it depends on the number of changes that need to be made. The default is 7 days.