## Sheet1
Second Language Teaching MA
Thesis Timeline
Student:
| 2021-07-14 | Goal for Defense: (Type in MM/DD/YYYY)
Days Left | Due Date | Task | Person | No. of Days
-45 | 2021-02-09 | Give Chair Prospectus | Chair | 3
|  | Make Revisions on Prospectus | Student | 2
-40 | 2021-02-14 | Give Committee Prospetus | Committee | 14
|  | Prospectus Meeting with Committee | Everyone | NA
|  | Make Revisions on Prospectus | Student | 2
-24 | 2021-03-02 | Give Committee Final Draft of Prospectus | Student | 2
|  | Write Draft of IRB Protocol | Student | 2
-20 | 2021-03-06 | Give Chair Draft of IRB Protocol | Chair | 3
|  | Make Revisions on IRB Protocol and Submit | Student | 2
-15 | 2021-03-11 | Give Chair Draft of Introduction | Chair | 3
|  | Make Revisions on Introduction | Student | 2
-10 | 2021-03-16 | Give Chair References | Chair | 3
|  | Make Revisions on References | Student | 3
|  | Collect Data (Pending IRB approval) | Student | 45
41 | 2021-05-06 | Give Chair Methodology Section | Chair | 3
|  | Make Revisions to Methodology Section | Student | 2
|  | Perform Analysis | Student | 14
60 | 2021-05-25 | Give Chair Findings Section | Chair | 3
|  | Make Revisions on Findings | Student | 2
65 | 2021-05-30 | Give Chair Literature Review | Chair | 3
|  | Make Revisions on Literature Review | Student | 2
70 | 2021-06-04 | Give Chair Introduction, Discussions and Conclusion | Chair | 3
|  | Make Revisions on Introduction, Discussions and Conclusion | Student | 2
75 | 2021-06-09 | Give Chair Complete Draft of Thesis | Chair | 3
|  | Make Revisions Complete Draft of Thesis | Student | 2
80 | 2021-06-14 | Give Committee Chair Approved Complete Draft of Thesis | Committee | 14
|  | Make Revisions based on Committee Recommendations | Student | 2
110 | 2021-06-30 | Get Approval from Committee for Defense | Committee needs defendable copy | NA
|  | Give Committee Defense-Ready Thesis | Committee needs defendable copy | 14
110 | 2021-07-14 | Thesis Defense
|  | Make Revisions on Thesis | Student | 7
131 | 2021-08-04 | Turn in Final PDF Version of Thesis for Department Approval | Student
Formulas:
Days Left = ([Due Date]-TODAY())
Due Date = B37-SUM([No. of Days]:E37)
Due Date = B37-SUM([No. of Days, row below]:E37)
Note on E38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There is no minimum timeline for this so the amount of time devoted to it depends on the number of changes that need to be made. The default is 7 days.